## Template
PM Essentials
Project Schedule
Template
Template Description
1 Purpose
The Schedule Template helps plan and track important tasks and dates within a project.
2 How to Use
The Project Schedule Template is pre-configured to align to a standard Project Management life cycle. Milestones, start and finish dates, and common activities are provided. Add or delete tasks and modify dates to make the schedule applicable to each project's needs. Add other columns to capture other details of the schedule.
3 Best Practice
Prepare a tentative project schedule in initiation and adjust throughout the life of the project. Baselining a project schedule should occur at the conclusion of planning but may occur in initiation and re-baselined at conclusion of planning dependent on organizations policies and project details. In an effort to capture project metrics (e.g. schedule variance) and continuously improve, all project schedules/plans should be baselined. The project schedule should be used as the single source of truth regarding project schedules, baselines, and project variances.
XLSX and MPP versions
Two versions of the PM Essentials Project Schedule Template are available. One is a Microsoft Project file (MPP) and the other an Excel spreadsheet (XLSX, which you are currently viewing). The Microsoft Project Schedule allows you to plug in dates, resources, and budget information. Once populated with dates and resources, key performance indicators (KPIs) such as schedule variance and % complete, can then be used to help track the project performance. The XLSX version provides basic scheduling functionality without automation.
Note: The PM Essentials Project Schedule Template is customizable as you see fit, on a per project basis, meeting specific needs of the project and/or your organization’s policies. The below sections are suggestions but can be tailored as applicable.
**NOTE: Please remove this page and any content in brackets [ ] when creating your Schedule Template.**
If you have any questions on PM Essentials or on project management practices, please contact DIR’s PPMO at ppmo@dir.texas.gov.

## Schedule
ID | % Complete | Task | Resource Names | Duration (days) | Start Date | Finish Date | Predecessors | Notes
1 |  | [Name of Project] |  | 168 | 2021-09-01 | 2021-09-23
2 |  | Initiation |  | 17 | 2021-09-01 | 2021-09-23
3 |  | Review Business Case Request (BCR) & Pre-Project Assessment (PPA) |  | 1 | 2021-09-01 | 2021-09-01
4 |  | Review Lessons Learned Repository |  | 1 | 2021-09-01 | 2021-09-01
5 |  | Create Project Charter |  | 5 | 2021-09-02 | 2021-09-08 | 4
6 |  | Create Draft of Project Schedule (.mpp) |  | 5 | 2021-09-09 | 2021-09-15 | 5
7 |  | Milestone: Obtain approval on Project Charter |  | 5 | 2021-09-16 | 2021-09-22 | 6
8 |  | Milestone: Conduct Project Kickoff (if applicable) |  | 1 | 2021-09-23 | 2021-09-23 | 7
9 |  | Planning |  | 105 | 2021-09-24 | 2022-02-17
10 |  | Define Project Scope |  | 5 | 2021-09-24 | 2021-09-30 | 8
11 |  | Formalize WBS/Project Schedule |  | 5 | 2021-10-01 | 2021-10-07 | 10
12 |  | Estimate Costs |  | 5 | 2021-10-08 | 2021-10-14 | 11
13 |  | Develop SOW/Plan Procurement (if applicable) |  | 60 | 2021-10-15 | 2022-01-06 | 12
14 |  | Approval of SOW (if applicable) |  | 10 | 2022-01-07 | 2022-01-20 | 13
15 |  | Obtain Resources and Team Members |  | 10 | 2022-01-21 | 2022-02-03 | 14
16 |  | Develop Communication Plan |  | 10 | 2022-02-04 | 2022-02-17 | 15
17 |  | Develop Business Requirements (if applicable) |  | 40 | 2021-10-01 | 2021-11-25 | 10
18 |  | Milestone: Conduct Project Kickoff (if applicable) |  | 1 | 2021-10-11 | 2021-10-11 | 18
19 |  | Execution |  | 126 | 2021-10-08 | 2022-04-01
20 |  | Conduct Procurements (if applicable) |  | 30 | 2022-01-21 | 2022-03-03 | 14
21 |  | Develop Business Requirements (if applicable) |  | 40 | 2021-10-08 | 2021-12-02 | 11
22 |  | Design |  | 20 | 2021-12-03 | 2021-12-30 | 22
23 |  | Develop or build |  | 20 | 2021-12-31 | 2022-01-27 | 23
24 |  | Test or verify |  | 30 | 2022-01-28 | 2022-03-10 | 24
25 |  | Customer acceptance |  | 1 | 2022-03-11 | 2022-03-11 | 25
26 |  | Release Activities |  | 10 | 2022-03-14 | 2022-03-25 | 26
27 |  | Post Release Activities |  | 5 | 2022-03-28 | 2022-04-01 | 27
28 |  | Closure |  | 15 | 2022-04-04 | 2022-04-22
29 |  | Complete Procurement Closure tasks (if applicable) |  | 5 | 2022-04-04 | 2022-04-08 | 28
30 |  | Provide Stakeholder Names for Customer Satisfaction Survey |  | 10 | 2022-04-04 | 2022-04-15 | 28
31 |  | Document Lessons Learned including results from Customer Satisfaction Survey |  | 5 | 2022-04-18 | 2022-04-22 | 31
32 |  | Seek Sponsor and Business Owner approval to close project |  | 5 | 2022-04-04 | 2022-04-08 | 28
33 |  | Complete Project Closure Template |  | 1 | 2022-04-11 | 2022-04-11 | 33
34 |  | Archive Project Documents and Artifacts |  | 1 | 2022-04-12 | 2022-04-12 | 34
35 |  | Mark Project as Completed |  | 1 | 2022-04-13 | 2022-04-13 | 35