## Slide 1: Writing an Effective Statement of Work Parts 1 & 2
DIR Connect
May 25, 2016
Notes: Module Title: DBITS Contract Utilization and Management

## Slide 2: DIR Conference Speakers
Shannon Kelley
Manager Enterprise Contract Management
Elizabeth Lopez
Contract Manager Enterprise Contract Management

## Slide 3: AGENDA
Statement of Work
  Standard elements of an SOW
  SOW Lifecycle
Plan the SOW
  Building the SOW
  Other Planning Considerations
Select the Vendor
  Best Practices for using DIR contracts
Manage the SOW
  Managing the SOW
  Dealing with Changes
  Issues & Disputes

## Slide 4: STATEMENT OF WORK
Standard Elements of an SOW

## Slide 5: Statement of Work Defined
A Statement of Work (SOW) is a formal document that captures and defines the work that must be performed to meet a Customer’s needs
Not only does a SOW provide a commitment for all parties involved in a project, it forms the basic framework of a Contract
SB 20, Sec. 2157.0685
"statement of work" means a document that states the requirements for a contract, including deliverables, performance specifications, and other requirements, specific to the vendor under that contract …

## Slide 6: DIR Contract Categories Appropriate for SOWS
DIR has established contracts that prequalify vendors to respond to SOWs across a variety of technology categories, including:
  Deliverables Based Information Technology Services (DBITS)
  Managed Services for Information Technology
  Comprehensive Web Development
  IT Security Services
  Cloud Services

## Slide 7: SOW Elements
While a Statement of Work is unique for each project, SOW elements are generally consistent across projects:
  Scope of Project
  Roles and Responsibilities
  Deliverables
  Schedule
  Performance and Service Levels
  Acceptance Criteria
  Pricing and Payment Schedules/Milestones
  Assumptions

## Slide 8: SOW Elements
Additional Considerations:
  Submission/Format
  Reports and Meetings
  Period of Performance
  Customer Furnished Equipment and Workspace
  Additional Terms and Conditions
Notes: Minimum suggested items in the Statement of Work template include:
Scope of work
Project risks, assumptions and constraints
Roles and responsibilities
Detailed description of deliverables
Acceptance criteria, including testing or period of review
Project completion criteria
Project schedules to be achieved by vendor
Relevant quality processes

## Slide 9: SOW Lifecycle
This training establishes best practices in the Statement of Work lifecycle:
  The planning responsibilities to begin with the right foundation
  The intended selection approach to be leveraged by agencies
  The best practices in vendor management to agreed outcomes

## Slide 10: SOW Lifecycle
PLAN
○Define need
○Assess project risk
○Develop SOW elements
necessary to manage
the contract
SELECT
○Submit SOW to
appropriate categories
○Review responses
○Initiate work with the
selected vendor
MANAGE
○Develop tools necessary
to manage the vendor
○Document vendor
performance

## Slide 11: PLAN
Building the Statement of Work
Notes: Section Title: Plan | Building a Statement of Work

## Slide 12: Project Scope
In developing the project scope, key questions to ask are:
  Who needs to be on the team to make this succeed?
  Can we scope something we can manage?
  Can we identify risks in order to mitigate them?
  Can we build elements into the SOW to help us manage?

## Slide 13: The Iron Triangle (and when it’s not iron)
Traditional Statements of Work are legally enforceable agreements to transact business in a combination of scope, schedule and budget
A clear scope, schedule and budget are core to good planning and effective management of the
Statement of Work
Acceptance criteria is the glue that holds
it all together

## Slide 14: Who Carries the Risk?

## Slide 15: Brainstorming Project Goals and Objectives
Start by asking and answering basic questions:
  What does COMPLETE look like and how will we
  know we’re there?
  How will we measure success?
  What are the milestones that we will need to identify to measure progress?

## Slide 16: Essentials of a SMART* Objective
SMART
To grow online registration by 5%, by fiscal year end
To reduce licensure wait time to less than 2 minutes, by the end of June
To double our capacity to deliver benefit disbursements by November 1
NOT SO (SMART)
Maximize potential of agency website traffic
Improved operational performance management through increased automation
Website optimization through user friendly interfaces
SMART* (Specific, Measurable, Achievable, Realistic, and Timely)

## Slide 17: Getting to the Right Scope
Defining the project scope is a progressive elaboration of the requirements of the product(s) or service(s) that are needed to satisfy the project objectives
  Working with stakeholders, the Project or Contract Manager should facilitate open dialogue to elicit the product or service requirements
  This process should encourage discussion and seek clarification to ensure the project team fully understands the requirements
  Through effective elicitation techniques, the team can develop a set of precise, accurate, and comprehensive requirements

## Slide 18: Getting to the Right Scope (cont.)
The project scope should :
  describe the outcomes, or deliverables, and NOT the tasks
  specify requirements of project work products, such as the management plan, schedule, and milestones
More information and additional resources on requirements gathering is provided as a training handout

## Slide 19: Example: From Goal to Objectives
A goal of the Texas Department of Government Records (TDGR) is to promote openness and accountability in state government
To meet this goal, TDGR has launched an IT transformation project. The project’s objectives are:
  To develop and implement a statewide eDiscovery strategy by March 1, 2017,
  To transition 25% of the state’s permanent records to an electronic format by Q3 FY 2017, and
  To realign its technology workforce and processes to provide direct support to all state agencies by Q3 FY 2018

## Slide 20: Example: From Objectives to Scope
To implement the objectives of this project, TDGR has engaged stakeholders
To advance its transformation effort, TDGR plans to assess its current technology organization
TDGR has determined that it will obtain the services of a DIR vendor, but first, TDGR will scope the project and define the project’s deliverables by developing a Work Breakdown Structure (WBS)

## Slide 21: Example: From Scope to Deliverables
Create a deliverables oriented WBS
Identify what’s in scope and what’s not in scope
Identify the project deliverables
Establish a basis to create acceptance criteria, project milestones, and schedule

## Slide 22: Example: From Scope to Deliverables

## Slide 23: Example: From Deliverables to Acceptance
NO. | DELIVERABLE NAME | WBS# | DUE DATE | ACCEPTANCE CRITERIA
1 | Customer Survey on IT Services and Support | 1.1.1 | I week after project start date | 20-30 scaled questions reflecting performance attributes set forth in AMA Handbook for Customer Satisfaction
2 | Competency Assessment | 1.1.2 | As specified in Project Work Plan (see also 4.2.1 key Milestones Timeline) | Generic, Managerial and Technical Competency Mapping to Organizational Strategies, Mapping must provide detail at each level of Core, Business, Team and Role
3 | Current State Assessment Report | 1.1.3 | As specified in Project Work Plan (see also 4.2.1 Key Milestones Timeline) | - Identification of existing processes , desired outcomes, processes to achieve the desired outcomes - Identification and description of gaps - Description of means to fill gaps and requirements to bridge gaps

## Slide 24: Writing an Effective Deliverable
A deliverable should:
      be related to the project objectives
      provide unambiguous and sufficient detail
      describe a standard for performance
      provide a means to trace and monitor requirements
      be tied to a compensation structure that is consistent with the work performed

## Slide 25: Roles and Responsibilities
Detail for both customer and vendor
Examples:
Customer Roles and Responsibilities
  Site access at all three locations
  Purchase and delivery of network equipment
  Configuration design for all network equipment
Vendor Roles and Responsibilities
  Respond to network outages in accordance with SLA’s
  Respond to customer requests in accordance with SLA’s
  Provide any network drawing updates as changes occur

## Slide 26: Schedule
Include a timeline of the project with critical milestones/deliverables noted.
Examples:
This could be as detailed as a Microsoft Project schedule, or it may be as simple as a start and end date.
A Schedule may include a list of deliverables with dates (e.g., “Deliver three security forums and three web forums prior to June 15, 2014.”)

## Slide 27: Service Levels/Service Level Agreements
Service Levels enable the customer to specify service level expectations for the services being performed. They may be tied to response times for service, uptime of a network, mean time to repair (MTTR), or similar measures.
Examples:
Vendor will respond to outages within two hours of notification.
Vendor will provide a status within 4 hours of outage notification.

## Slide 28: Assumptions
This is a list of assumed actions that may be directly or indirectly related to the project that either the customer or the vendor want to note in writing before the project starts.
Examples:
Assume all equipment to be inventoried will be on respective site.
Customer will procure all necessary equipment for project.

## Slide 29: PLAN
Other Planning Considerations
Notes: Section Title: Plan | Other Planning Considerations

## Slide 30: Integrate Best Planning Practices
Engage appropriate stakeholders
Provide clear presentation of project management activities such as scope, schedule, and roles and responsibilities
In planning the SOW, please note, vendor cannot write specifications and participate in the procurement.

## Slide 31: Adhere to Statutory Requirements
Determine whether the project is subject to agency or agency and statewide project delivery requirements such as:
  QAT reporting requirements (TGC §2054.003 (10))
More information and additional resources on these requirements is provided as a training handout
Statement of Work review requirements per Senate Bill 20 (84R) – for state agencies only, excluding higher education

## Slide 32: OTHER RESOURCES
TPASS Contract Management Guide - provides best practices for contract management, including:
    procurement methods
    conducting risk analysis
    performance monitoring
Texas Project Delivery Framework (as applicable)
  Establishes a consistent, statewide method for project selection, control, and evaluation for major information resources projects

## Slide 33: SELECT
Best Practices for Evaluating Responses
and Selecting a Vendor
Notes: Section Title: Select | Best Practices for Using the DBITS Contract

## Slide 34: Submitting Your SOW to the Vendor Pool
Select vendors to receive SOW
May send to ALL vendors in the Technology Category
Goal is to ensure competition and provide Customer greatest opportunity for achieving the best solution at the best value
State agencies must follow SB 20 thresholds

## Slide 35: SB20 Changes for State Agencies Only
Contract Value | Number of DIR Vendors
$50,000 or less | May directly award the contract to a single vendor on the DIR list
More than $50,000 to $150,000 | Must submit to three vendors (or all DIR Vendors in a category with less than three vendors)
More than $150,000 to $1 million | Must submit to six vendors (or all DIR Vendors in a category with less than six vendors)
More than $1,000,000 | Agencies must conduct an independent procurement and cannot use DIR Cooperative Contracts

## Slide 36: Evaluating Responses
Vendors may only provide services in awarded categories/contract types. Check the contract (for DBITS) or Appendix C, Pricing Index for details
Customers should include in the SOW what criteria they will use to evaluate vendor responses
Customer should document the evaluation and award decision

## Slide 37: Negotiating With The Vendor
Customer should negotiate pricing directly with the vendor
Customer should ensure that the vendor is not making changes to SOW elements meant to be used to manage the relationship later
Customer may negotiate terms and conditions of an SOW to suit their business needs, HOWEVER…Negotiated terms and conditions MUST NOT conflict with or weaken the terms of the DIR Contract

## Slide 38: Award
To be awarded a Purchase Order, the vendor must respond, in writing, to the SOW for services as issued by customers, consistent with the Terms and Conditions of the contract.
The resulting contract or SOW Agreement should contain concise, active voice, e.g. The Vendor shall/must/will …
Ensure vendor’s Texas Franchise Tax status is Active and Vendor is not on the Exclusions List (System for Award Management), Texas Debarred Vendor List, and Sanctions List.

## Slide 39: Initiating Work
The vendor may begin work ONLY after receiving:
  An SOW signed by authorized representatives of both the Customer and the Vendor
  Agencies only - If SOW total is $50K - $1 million, DIR signature is also required
  AND a Purchase Order from the Customer
The value of any one SOW may not exceed $1 million including all extensions, renewals and change orders ($10 million for non-state agencies)
See DIR website for more information on SB20 changes and SOW review process.

## Slide 40: MANAGE
Managing the Statement of Work

## Slide 41: The Work Is Just Starting
After award, the focus turns to managing to the outcomes in accordance with:
  Defined scope
  Defined acceptance criteria at an agreed to price
  Specified milestones

## Slide 42: SOW Initiation Meeting
Purpose of an SOW Initiation Meeting is to ensure common understanding with regard to:
  Goals and the expected results of the project
  Performance requirements
  Roles and responsibilities of all parties
  Clarify escalation processes

## Slide 43: Contract Managers Wear Many Hats
Notes: Contract Manager’s Role – Many Hats
Cop on the beat
  Keep bad things from happening
  Enforce the rules
Detective
  Why didn’t this happen the way you said it would?
  Just one more thing…
Air Traffic Controller
  Ensure many complicated things happen according to rules of engagement
  Respond rapidly to avoid catastrophes
Coach
  Manage a system that requires everyone to perform
  Direct the team to win the game

## Slide 44: Monitoring Responsibilities
Schedule
  Achievement of major milestones and overall project pace
Budget
  Review cost variances
Quality
  Performance against agreed specifications and delivery
Risk
  Identify outstanding actions

## Slide 45: Documenting Vendor Performance
There are numerous ways to document vendor performance:
  Compliance Record
  Summary Evaluation Report
  Vendor Performance Report
For all Purchase Orders exceeding $25,000, state agencies must report vendor performance to the Texas Comptroller’s Office in the Vendor Performance Tracking System (TGC §2262.055 and 34 TAC §20.108)
The Comptroller’s Office instructs agencies that vendor performance should be reported not later than 30 days after completion of the purchase or service.

## Slide 46: MANAGE
Dealing with Changes
Notes: Section Title: Manage | Dealing with Changes

## Slide 47: Best Practice for Changes
Document procedures for ordering changes in the SOW
Change orders typically represent instructions from the Customer to Vendor to change tasks (although both parties can initiate a change order)
Formal Changes, often referred to as Amendments, are changes to the original SOW resulting from the Contract Manager’s actions or directions that impact the cost or schedule for performance
Amendments require a Purchase Order Change Notice (POCN) http://comptroller.texas.gov/procurement/tools/proc_forms/index.html
For state agencies amendments/changes in scope must go through the DIR SOW review process

## Slide 48: Verbal Change Orders are Unenforceable
It’s important to not introduce additional risk through unintentional actions that may affect the SOW
Retain the power of the SOW by adhering to, and managing to, the provisions of the SOW
An amendment to an SOW must specify that it holds the highest order of precedence in that SOW

## Slide 49: First, Best Choice: Managing to the Deliverables
If deliverables do not meet quality standards, the
Customer does not have to accept them
Vendor has to remedy identified defects
Since payments are tied to acceptance, then the Customer does not pay until they are accepted

## Slide 50: MANAGE
Issues & Disputes
Notes: Section Title: Manage | Issues & Disputes

## Slide 51: Managing Issues & Disputes
Effectiveness in which issues and disputes are managed may be tied to the extent they were addressed in the Planning phase
Customer should always seek the most effective way to
  Address the issue AND
  Get project performance back on track to effectively deliver the goods or services in the contract WHILE
  Maintaining a positive working relationship

## Slide 52: Corrective Action Plan
If quality suffers and/or project starts to drift, Customer can require a Corrective Action Plan:
  Customer identifies deficiencies
  In response, Vendor describes the corrective action that will be taken
  Corrective Action Plan is incorporated in the SOW and action items are tracked

## Slide 53: Termination
In extreme cases it may be necessary to end a Statement of Work before the period of performance ends
Two forms of termination:
Termination should begin only after sufficient consideration and consultation

## Slide 54: Termination for Convenience
Termination for Convenience allows Customer to end the SOW at its discretion with no cause:
  May occur when the scope of the project changes and future work is no longer required
  Invoking Termination for Convenience isn’t always “free”

## Slide 55: Termination for Cause
Termination for Cause allows either party the right to cancel the SOW due to failure of the other party to execute to SOW requirements
If initiated by Customer, Termination for Cause requires Customer to demonstrate that the Vendor will be unable to cure the performance issues identified

## Slide 56: Issue Escalation*
Attempt to resolve with vendor’s first tier management
Contact higher level manager
Hold meeting. Legal representation may be necessary.
Contract Manager works with Purchaser and Legal to initiate steps toward SOW Termination.
Action is taken in accordance with SOW provisions and applicable laws.
*VPTS

## Slide 57: QUESTIONS?
Elizabeth Lopez, Contract Manager
Enterprise Contract Management
elizabeth.lopez@dir.texas.gov
Shannon Kelley, Manager
Enterprise Contract Management
shannon.kelley@dir.texas.gov
Tom Niland, Program Director
Statewide Project Delivery Framework
tom.niland@dir.texas.gov
Notes: Contact Info:
Aiko Neill, DBITS Contract Manager
Department of Information Resources
aiko.neill@dir.texas.gov